## User Stories
ID | Story | Sprint | Priority | Status | Points
001 | As a member of a shared living space, I want to keep track of communal living expenses in order to stop relying on the “I owe you” system between everybody. | 2,3 | High | In Progress | 20
002 | As a member of a shared living space, I want to be able to estimate how much will owe for my portion of the monthly bills so that I can properly set aside/save funds in advance. | 2,3 | Medium | In Progress | 15
003 | As someone with many different types of expenses, I want to be able to manually track other types of expenses and bills and which roommates are responsible for them, so that I manage all my expenses. | 2,3 | High | In Progress | 15
004 | As a user I want to be able to set the amount each person owes for each bill by splitting evenly, setting specific dollar amounts, or assigning percentages so that I can fairly assign payments between roommates. |  | High | Waiting | 5
005 | As a user with many different expenses, I want to be able to see how much I owe over certain time periods (monthly, weekly, etc.) and who is charging me for what so that I can be sure I am being charged correctly. |  | Medium | Waiting | 10
006 | As a user, if I don’t have the cash to pay bills on time I’d like to be able to pay either in order of a) the age of the debt, or b) my own set priorities. These would allow convenience to me, and fairness to my creditors. |  | Medium | Waiting | 10
007 | As a user I want to be able to input payments I make in person (via cash or check) so that I have flexibility in my payment options. |  | High | Waiting | 5
008 | As user I want to be able to dispute charges and message who ever assessed them if they aren’t correct so that I don’t get charged incorrectly and can resolve the problem anywhere. |  | Medium | Waiting | 10
009 | As a member of a shared living space, I want to have a communal shopping list to track what need to be purchased and who gets charged for the purchases so the time without certain items is reduced and everyone charged fairly. | 3 | High | In Progress | 20
010 | As a member of a shared living space, I want a communal “bulletin board” board to post messages for the room (e.g. take out the trash, clean dishes etc) to communicate with all roommates more easily. |  | Low | Waiting | 15
011 | As someone with several shared spaces I want to be able to create my own “room” so I can add and remove members as needed. | 3 | High | Waiting | 10
012 | As a user I want to be able to access the site from anywhere without any geographic requirements or too much validation of location so that my privacy is protected. |  | Medium | Waiting | 10
013 | As a user I want the ability to make electronic payments via credit card, so I can pay my roommates at my convenience without needing to carry cash |  | Medium | Waiting
014
015
016
017
018
019
020
021
022
023
024
025
026
027
028
029
030
031
032
033
034
035
036
037
038
039
040
041
042
043
044
045
046
047
048
049
050
051
052
053
054
055
056
057
058
059
060
061
062
063
064
065
066
067
068
069
070
071
072
073
074
075
076
077
078
079
080
081
082
083
084
085
086
087
088
089
090
091
092
093
094
095
096
097
098
099
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299