## Sprint 1
ID | Story | Type | Subtype | Priority | Story points | Member | Contribution
001 | As a member of a shared living space, I want to keep track of communal living expenses in order to stop relying on the “I owe you” system between everybody. | Functional | Technical work | High | 20 | Josh | Linked FireAuth
002 | As a member of a shared living space, I want to be able to estimate how much will owe for my portion of the monthly bills so that I can properly set aside/save funds in advance. | Functional | Technical work | Medium | 15
003 | As someone with many different types of expenses, I want to be able to manually track other types of expenses and bills and which roommates are responsible for them, so that I manage all my expenses. | Functional | Technical work | High | 15 | Durgin | Domain coding
004 | As a user I want to be able to set the amount each person owes for each bill by splitting evenly, setting specific dollar amounts, or assigning percentages so that I can fairly assign payments between roommates. | Functional | Technical work | High | 5 | Matt A | Charge subtypes
005 | As a user with many different expenses, I want to be able to see how much I owe over certain time periods (monthly, weekly, etc.) and who is charging me for what so that I can be sure I am being charged correctly. | Functional | Technical work | Medium | 10
006 | As a user, if I don’t have the cash to pay bills on time I’d like to be able to pay either in order of a) the age of the debt, or b) my own set priorities. These would allow convenience to me, and fairness to my creditors. | Functional | Technical work | Medium | 10
007 | As a user I want to be able to input payments I make in person (via cash or check) so that I have flexibility in my payment options. | Functional | Technical work | High | 5 | Matt P | UI/Domain code
008 | As user I want to be able to dispute charges and message who ever assessed them if they aren’t correct so that I don’t get charged incorrectly and can resolve the problem anywhere. | Functional | Technical work | Medium | 10
009 | As a member of a shared living space, I want to have a communal shopping list to track what need to be purchased and who gets charged for the purchases so the time without certain items is reduced and everyone charged fairly. | Functional | Technical work | High | 20 | Aiden | Configuration
010 | As a member of a shared living space, I want a communal “bulletin board” board to post messages for the room (e.g. take out the trash, clean dishes etc) to communicate with all roommates more easily. | Functional | Technical work | Medium | 15
011 | As someone with several shared spaces I want to be able to create my own “room” so I can add and remove members as needed. | Functional | Technical work | High | 10
012 | As a user I want to be able to access the site from anywhere without any geographic requirements or too much validation of location so that my privacy is protected. | Functional | Technical work | Medium | 10